## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 |  | Introduction to Project,AI,ML and Langchain | MUST HAVE | No Dependency | Raushan Kumar Gupta | 3- Completed
S2 | S2 |  | Understanding Memory, Types of memory: Conversation Buffer, Conversation Buffer Window, Entity, Conversation Summary, Conversation Summary Buffer | MUST HAVE | Gemini API | Raushan Kumar Gupta | 3- Completed
S3 | S3 |  | Exploring Agents, RAG, HuggingFace, Embeddings, Vector stores: Pinecone, Create Indexes, Retrieval | MUST HAVE | Pinecone | Raushan Kumar Gupta | 3- Completed
S4 | S4 |  | Building Project: Speech-To-Speech-Streaming | MUST HAVE | Gemini API | Raushan Kumar Gupta | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to Project | 2025-02-24 | 2025-02-25 | Raushan Kumar Gupta | Others | 3- Completed
|  | Build projects on memory and types of memory | 2025-03-04 | 2025-03-06 | Raushan Kumar Gupta | Coding | 3- Completed
|  | Build projects on Agent, RAG, Vector Store | 2025-03-18 | 2025-03-20 | Raushan Kumar Gupta | Coding | 3- Completed
|  | Build project: Speech-To-Speech-Streaming | 2025-03-22 | 2025-03-26 | Raushan Kumar Gupta | Coding | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentor and team
Sprint 2 | Day 8 | Lack of clarity on Conversation Summary Buffer | Discuss with Mentor
Sprint 3 | Day 13 | Not able to load multiple files from directory into Vector Store | Discuss with Mentor, Team and also Search on Google and AI models

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-02-24 | 2025-02-28 | Raushan Kumar Gupta | Basic Langchain Project | Issue with credentials | Created Google Cloud Account | installed credentials and included in my code
2 | 3 | 2025-03-17 | 2025-03-21 | Raushan Kumar Gupta | Vector Store Project | Issue with OpenAI Embedding | Explore and use HuggingFace Embedding | Discuss with Mentor and Team and explore HuggingFace Embedding Model
3
4
5
6
7